## Work Plan
Module | Deliverable | Backend detail | Owner | Timeline | Acceptance
M1 Auth & Roles | Single role list per user in the login response; no generic admin flag on non-admin accounts | Roles: admin, front_desk, engineer, qa, inventory_manager, sales. Token payload carries roles and assigned store/branch. | Backend | - | Each role resolves to exactly its own dashboard
M1 Auth & Roles | Server-side permission checks on every POS and operations endpoint | Sales: POS, orders, follow-ups, warranty. Admin: all, refund approval, price override, discounts above limit. Front desk: follow-ups, warranty, customers. Others: 403. | Backend | - | Sales user calling an admin endpoint gets 403
M2 Catalog & Serialized Stock | POS product catalog endpoint backed by Odoo products | Name, SKU/barcode, price, tracking (none or serial), stock on hand per branch; reuse the existing parts-catalog data source where it fits. | Backend / Odoo | - | Catalog matches Odoo; barcode scan resolves a product
M2 Catalog & Serialized Stock | Serialized units (serial number, IMEI, IMEI2, status) | Per-unit availability, one unit can be on only one open sale, held sale or reserved order; unit lookup by any identifier. | Backend / Odoo | - | A unit cannot be sold twice, including from two tills at once
M2 Catalog & Serialized Stock | Warranty policy per product and per unit | Type, provider, duration in months, starts on sale or fixed date, terms. | Backend / Odoo | - | Policy returned with the product
M3 Sales (Checkout) | Create sale endpoint with atomic validation | Lines, price snapshot, order-level discount, split payments totalling the sale total, cashier, branch, channel, note. Customer name and phone required for serialized devices. Reject unavailable units. | Backend | - | Invalid or duplicate submissions are rejected with clear messages
M3 Sales (Checkout) | Sale numbering | Sequential per day, e.g. SALE-YYYYMMDD-001, generated server-side, unique across all tills. | Backend | - | No duplicate or skipped numbers across two tills
M3 Sales (Checkout) | Idempotent submit and offline sync | Client-generated key so a retried or offline-queued sale posts once; endpoint returning sales not yet synced; sale list with filters (date, channel, cashier, customer, serial or IMEI, item). | Backend | - | A sale submitted twice is stored once
M3 Sales (Checkout) | Discount rules | Cashier limit 10% of subtotal; above that needs an admin; reason required; approver recorded. | Backend | - | Over-limit discount from a cashier is refused
M3 Sales (Checkout) | Price override restricted to admin | Unit price changes accepted only from admin accounts and audited. | Backend | - | Cashier price change is refused
M3 Sales (Checkout) | Receipt data | Receipt payload per sale: lines, discount, voucher, payments, change due, warranty details. | Backend | - | Receipt reprint identical to original
M4 Payments & Cash Shifts | Shift open and close | One active shift per cashier; opening float; closing float; expected cash = float + cash sales - cash refunds; variance stored. | Backend | - | Variance matches the manual count
M4 Payments & Cash Shifts | Payments stamped to the shift | Methods: cash, POS terminal, bank transfer; each payment carries time and shift; sales blocked without an active shift. | Backend | - | Shift report totals equal the payments taken
M4 Payments & Cash Shifts | Shift history and end-of-shift summary | Cash sales total, cash refunds total, expected cash, variance per shift. | Backend | - | History matches closed shifts
M5 Held Sales | Hold, resume and discard | Parked cart with label, customer, note; held units are reserved so another till cannot sell them; resume removes the hold. | Backend | - | Held unit unavailable elsewhere until resumed or discarded
M6 Reserved Orders | Reserve order with deposit | Lifecycle: reserved, completed, cancelled; collection due date; deposit as first payment; customer name and phone required. | Backend | - | Reserved order shows balance and due date
M6 Reserved Orders | Order balance payments, collection and cancellation | Add payments until balance is zero; collection recorded with actor and identity-verified flag; cancel only when unpaid. | Backend | - | Cannot collect with an outstanding balance or without verification
M7 Refunds & Returns | Refund by line and quantity | Value prorated for the order discount; limited to quantity not already refunded; specific serialized units named. | Backend | - | Total refunds never exceed what was paid
M7 Refunds & Returns | Approval and repayment workflow | Refunds above NGN 50,000 raised by non-admins need admin approval before repayment; statuses pending, paid, cancelled; repayment reference for card or bank refunds; cash refunds linked to the shift. | Backend | - | Unapproved large refund cannot be paid
M7 Refunds & Returns | Return condition and stock effect | Resellable returns to stock; faulty and not-returned handled separately; deposit refunds for cancelled reserved orders. | Backend / Odoo | - | Stock and Odoo agree after a return
M8 Vouchers (Odoo) | Validate voucher endpoint | POST /api/v1/sales/vouchers/validate/ with code, subtotal, cart lines; returns voucher_code and discount_amount, or an error message (invalid, expired, used, minimum spend, product not eligible). | Backend / Odoo | - | Valid code discounts the cart; bad code gives a clear message
M8 Vouchers (Odoo) | Redeem on sale completion | Mark the code used in Odoo once, atomically, with the sale reference; safe against two tills redeeming together; conflict returned if used between validation and payment. | Backend / Odoo | - | Two tills cannot redeem one single-use code
M8 Vouchers (Odoo) | Voucher on the sale record and refunds | Store voucher code and discount on the sale; refund rule on whether a voucher is reinstated. | Backend / Odoo | - | Refunded sale follows the agreed rule
M9 Audit Log | Immutable audit trail | Records: discount applied, price change, refund created, approved or rejected, voucher redeemed, collection, order cancelled, shift open and close; actor, time, detail. | Backend | - | Entries cannot be edited or deleted
M10 Customers | Customer directory | Created from sales, enquiries and manual entry; duplicates matched by normalised phone; email optional; customer history (sales, enquiries, repairs, refunds). | Backend | - | Same phone number never creates two customers
M11 Enquiries & Follow-ups | Enquiry records | Customer, request, owner, follow-up date; statuses open, converted, lost; outcome note. | Backend | - | Overdue follow-ups are queryable
M11 Enquiries & Follow-ups | Contact log and rescheduling | Each contact: time, user, channel (call, WhatsApp, SMS, email, visit), note; reschedule with new owner. | Backend | - | Contact history kept per enquiry
M11 Enquiries & Follow-ups | Close as converted linked to a completed sale | A converted enquiry must reference a completed sale for that customer. | Backend | - | Cannot convert without a linked completed sale
M12 Warranty | Sale warranty activation | Starts at sale or fixed date, expiry calculated, snapshot stored per serialized unit at sale time. | Backend | - | Expiry date matches policy
M12 Warranty | Repair coverage records | Record post-repair coverage (months, terms, recorded by, completion date) once per repair. | Backend | - | Second record for the same repair is rejected
M12 Warranty | Warranty lookup and linking to repairs | Search by serial, IMEI, phone, name, sale or job reference; status active, expired or returned; link a record to a warranty repair ticket. | Backend | - | Lookup by any identifier finds the record
M13 Operations & Blockers | Work needing attention | Aggregates reserved orders (balance due, paid but uncollected), open repairs by stage, open and overdue follow-ups, pending refunds (awaiting approval or repayment). | Backend | - | Counts match the underlying records
M13 Operations & Blockers | Owner, next action and due date per item | Assign and update; non-admins see their own items (front desk also sees front-desk items). | Backend | - | Assignment visible to the owner
M14 Reporting & Revenue | Sales summary endpoint | Ranges today, 1d, 3d, 7d, 30d, 90d, all plus week and previous week; gross, refunds, net, count, average value, top items, channel breakdown, by salesperson, by branch. | Backend | - | Totals equal the sum of sale records
M14 Reporting & Revenue | Repair sales (job revenue) ranges | Extend /jobs/admin/dashboard/stats/ with today, week, previous_week, 60d; one written definition of revenue (diagnosis, repair payments, vouchers, refunds). | Backend | - | Same figure on Dashboard, Finance, Sales and Operations
M14 Reporting & Revenue | Revenue reconciliation | Total revenue = jobs + in-store + website, computed once server-side and reused by every page; excludes demo records. | Backend / Finance | - | All pages agree to the naira
M15 Website Sales (Odoo) | Website sales summary | GET /api/v1/sales/website/summary/?range=... returns count and revenue from Odoo website orders; confirmed order states only; excludes cancelled and refunded. | Backend / Odoo | - | Website figures match Odoo
M15 Website Sales (Odoo) | Website sales in the sales list | Website orders returned with channel = website so the Sales page can filter them. | Backend / Odoo | - | Channel filter works
M16 Odoo 19 Integration | Connection and credentials | Service account, secure secret storage, API client with timeouts and retries, separate sandbox and production. | Backend / Odoo | - | Sandbox and production both reachable
M16 Odoo 19 Integration | Master data sync | Products, prices, stock, branches and warehouses, customers (partners), vouchers/loyalty programs from Odoo; scheduled plus on-demand refresh. | Backend / Odoo | - | Changes in Odoo appear in the POS
M16 Odoo 19 Integration | Posting POS sales to Odoo | Decide POS module versus sale.order; create orders or invoices, payments by method, stock moves, serial numbers, discounts, vouchers; branch and cashier mapped. | Backend / Odoo | - | Stock reduces and daily totals match Odoo
M16 Odoo 19 Integration | Posting refunds, returns and reserved orders | Credit notes and return stock moves; reserved orders as quotations or orders with deposit payments. | Backend / Odoo | - | Refund shows as a credit note in Odoo
M16 Odoo 19 Integration | Outbox, retries and error queue | Queue of items to post, retry with backoff, no duplicates, failed items visible to admin with reason and a retry button. | Backend | - | Nothing lost or posted twice when Odoo is down
M16 Odoo 19 Integration | Daily reconciliation job | Compare POS totals, stock and vouchers with Odoo per branch per day; report differences. | Backend / Finance | - | Report shows zero unexplained differences
M17 Data Migration | Import sales already stored on devices | Export from each device, validate, load once, flag as migrated; skip demo records. | Backend / Frontend | - | Imported totals match device totals
M18 Security & Operations | Access control, validation and rate limits | Input validation on every endpoint, branch scoping for non-admin users, protection against replay and double submission. | Backend | - | Security review passed
M18 Security & Operations | Logging, monitoring and backups | Request and error logging, alerts on failed Odoo posts, database backups and restore test. | Backend | - | Alerts fire on a forced failure
M19 Testing & Release | Automated tests | Unit and API tests per module, concurrency tests for units, vouchers and shifts, Odoo sandbox tests. | Backend / QA | - | All pass in CI
M19 Testing & Release | API documentation | OpenAPI spec for every endpoint, request and response examples, error codes. | Backend | - | Frontend team signs off the spec
M19 Testing & Release | UAT, staged release and handover | Test accounts per role, UAT script, staging then production, rollback plan, runbook. | Backend / QA | - | UAT passed; live in production

## API Endpoints
Module | Endpoint (proposed) | Purpose
Sales | POST /api/v1/pos/sales/ | Create sale (idempotent)
Sales | GET /api/v1/pos/sales/ | List and filter sales
Sales | GET /api/v1/pos/sales/{id}/ | Sale detail and receipt data
Catalog | GET /api/v1/pos/catalog/ | Products with stock and tracking
Catalog | GET /api/v1/pos/units/?q= | Serialized unit lookup
Shifts | POST /api/v1/pos/shifts/start/ | Open shift
Shifts | POST /api/v1/pos/shifts/{id}/end/ | Close shift
Shifts | GET /api/v1/pos/shifts/ | Shift history
Held sales | POST/GET/DELETE /api/v1/pos/held-sales/ | Hold, list, resume, discard
Orders | POST /api/v1/pos/orders/ | Reserve order
Orders | POST /api/v1/pos/orders/{id}/payments/ | Add payment
Orders | POST /api/v1/pos/orders/{id}/collect/ | Record collection
Orders | POST /api/v1/pos/orders/{id}/cancel/ | Cancel unpaid order
Refunds | POST /api/v1/pos/refunds/ | Raise refund
Refunds | POST /api/v1/pos/refunds/{id}/decision/ | Approve or reject
Refunds | POST /api/v1/pos/refunds/{id}/repay/ | Confirm repayment or cancel
Vouchers | POST /api/v1/sales/vouchers/validate/ | Preview discount from Odoo
Audit | GET /api/v1/pos/audit/ | Audit entries
Customers | GET/POST /api/v1/customers/ | Directory and create
Enquiries | GET/POST /api/v1/enquiries/ | List and create
Enquiries | POST /api/v1/enquiries/{id}/contacts/ | Log contact
Enquiries | POST /api/v1/enquiries/{id}/close/ | Convert or lose
Warranty | GET /api/v1/warranty/?q= | Lookup
Warranty | POST /api/v1/warranty/repair-coverage/ | Record repair coverage
Operations | GET /api/v1/operations/blockers/ | Work needing attention
Operations | PATCH /api/v1/operations/blockers/{id}/ | Owner, action, due date
Reporting | GET /api/v1/sales/summary/?range= | Sales summary
Reporting | GET /api/v1/sales/website/summary/?range= | Website sales
Reporting | GET /jobs/admin/dashboard/stats/?range= | Job (repair) revenue; add new ranges
Odoo admin | GET /api/v1/odoo/sync-queue/ | Failed and pending posts
Odoo admin | POST /api/v1/odoo/sync-queue/{id}/retry/ | Retry a post

## Risks
Risk | Impact | Mitigation
Odoo sandbox and API access not ready at start | Modules M2, M8, M15, M16 slip | Secure access first
Voucher rules undecided | M8 blocked | Business owner decides before M8 starts
Revenue definitions not signed off | Figures differ between pages | Finance signs off one definition (M14)
Same unit or voucher used by two tills | Double sale or double redemption | Atomic checks in the backend and Odoo, never only in the browser
Odoo unavailable during a sale | Lost or duplicate postings | Outbox with retries and idempotent keys (M16)
Offline tills | Vouchers and unit availability cannot be checked | Decide: allow and validate later, or block
Sales only on devices today | Data lost if a browser is cleared | Migrate early (M17)

## Decisions Needed
# | Decision | Owner | Answer
1 | Odoo voucher type used at the POS and rules per code | Business owner | -
2 | Does a refund reinstate its voucher | Business owner / Finance | -
3 | POS posts through Odoo's POS module or sales orders | Odoo developer / Finance | -
4 | Which order states count as a website sale | Finance | -
5 | May offline sales use vouchers | Business owner | -
6 | Are discount limit (10%) and refund approval limit (NGN 50,000) set in settings or fixed | Business owner | -